Estimated Time Allocation

Combined efforts in hours, with descriptions

Combined effort in hours, with description of sections and names against each section.

It should be noted that this is a plan and there are many circumstances that could affect how closely we follow this.  There will, of course, be a review at the end of the project.

Revision History

| 23/10/00 | Initial creation |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Committed by: | pjm2 | Verified by: | tdb1 |
|  |  |  |  | Date: | 24/03/01 |
|  |  | Committed by: |  | Verified by: |  |
|  |  |  |  | Date: |  |
|  |  | Committed by: |  | Verified by: |  |
|  |  |  |  | Date: |  |
|  |  | Committed by: |  | Verified by: |  |
|  |  |  |  | Date: |  |
|  |  | Committed by: |  | Verified by: |  |
|  |  |  |  | Date: |  |

Introduction	2

Management and Administration tasks (200 hours)	2

Webpages (10 hours)	2

CVS (10 hours)	2

Meetings/minutes/meetings with iau (180 hours)	2

Requirements, analysis, specification (85 hours)	2

Find out what the requirements are (5 hours)	2

Look at other systems (30 hours)	2

Analysing out own ideas (40 hours)	2

Produce specification (10 hours)	2

Design (200 hours)	2

UML (25 hours)	2

Interface design (20 hours)	2

Protocol design (30 hours)	3

Server design (30 hours)	3

GUI/Client design (20 hours)	3

Host design (10 hours)	3

Web Interface Design (35 hours)	3

DB Infrastructure (20 hours)	3

Implementation (300 hours)	3

QA, QC, Testing (195 hours)	3

Document specifications (5 hours)	3

Coding specifications and adherence (10 hours)	3

Testing of each of the modules (180 hours)	3

Documentation (150 hours)	3

User documents (40 hours)	3

Maintenance documents (60 hours)	3

Internal documents (50 hours)	3

# Introduction

This document lists our estimations of combined efforts in hours, with description of sections and names against each section.

It should be noted that this is a plan, and there are many circumstances that could affect how closely we follow this.  There will, of course, be a review at the end of the project.

## Management and Administration tasks (200 hours)

### Webpages (10 hours)

Creating and maintaining the website, as well as ensuring that everyone adheres to the same design – pjm2 (others contribute 50%)

### CVS (10 hours)

Setting up, managing and maintaining the CVS repository and related facilities.  Also assisting in the use of CVS – tdb1 (other contribute 50%)

### Meetings/minutes/meetings with iau (180 hours)

Attending regular meetings, both as a group and with iau.  Also taking of minutes in our group meetings and planning each meeting in advance – all members.

## Requirements, analysis, specification (85 hours)

### Find out what the requirements are (5 hours)

Find out exactly what the system needs to do, including meeting with jc.  Document these requirements in a requirements list – all members.

### Look at other systems (30 hours)

Research into similar products with the intention of seeing how our proposed idea compares and maybe get ideas for new features in the system – ajm4 & ab11.

### Analysing out own ideas (40 hours)

Looking at the merits/weaknesses of our ideas and helping to improve them.  Finding faults in our ideas will help to improve the final design – all members.

### Produce specification (10 hours)

Generating a relatively detailed specification of the overall system, from which UML designs can be made – tdb1 & pjm2.

## Design (200 hours)

### UML (25 hours)

Producing UML designs for the various parts of the system – ajm4.

### Interface design (20 hours)

Specifying the interfaces for communication between the various parts of the system – pjm2 & ab11.

### Protocol design (30 hours)

Specifying the protocol in detail for host to server communications and client to server communications – pjm2 & ab11.

### Server design (30 hours)

Designing the server and how the components plug together and interact – tdb1 & ajm4.

### GUI/Client design (20 hours)

Designing the GUI/Client side of the system – pjm2 & ab11.

### Host design (10 hours)

Designing the host application, which will require more work due to the C/C++ implementation language – ajm4 & tdb1.

### Web Interface Design (35 hours)

Designing the web front-end to the database, providing graphs and access to logs – pjm2.

### DB Infrastructure (20 hours)

Setting up the database, tables and deciding how they should be arranged.  Database design principles should be put into practice – pjm2.

## Implementation (300 hours)

Our implementation sections will be detailed in a separate document in some detail.

## QA, QC, Testing (195 hours)

### Document specifications (5 hours)

Producing a proper specification that all of our documents should follow – pjm2.

### Coding specifications and adherence (10 hours)

Producing a coding specification and ensure all code adheres to it – all members.

### Testing of each of the modules (180 hours)

Testing each part of the system, preferably with good testing rigs – all members.

## Documentation (150 hours)

### User documents (40 hours)

Documentation for the user – ajm4 & tdb1.

### Maintenance documents (60 hours)

Documentation for the maintainer and possible future developers – all members.

### Internal documents (50 hours)

Internal documentation made during the course of the project – all members.